## Portfolio Tracker
Portfolio Start Date |  |  | 2016-09-01
# | Project | RAG | Start | End | % Complete | Budget | Spend | 2016-09-30 | 2016-10-31 | 2016-11-30 | 2017-01-31 | 2017-02-28 | 2017-03-31 | 2017-04-30 | 2017-05-31 | 2017-06-30 | 2017-07-31 | 2017-08-31 | 2017-09-30 | 2017-10-31 | 2017-11-30 | 2017-12-31 | 2018-01-31 | 2018-02-28 | 2018-03-31 | 2018-04-30 | 2018-05-31 | 2018-06-30 | 2018-07-31 | 2018-08-31 | 2018-09-30
1 | Mercury | 1 | 2016-10-23 | 2017-05-15 | 50% | 100000 | 10000 | bar: 2016-10-31
2 | Venus | 2 | 2016-12-13 | 2017-10-15 | 30% | 200000 | 60000 | bar: 2017-01-31 to 2017-02-28
3 | Earth | 3 | 2016-11-23 | 2017-08-21 | 40% | 350000 | 300000 | bar: 2016-11-30 to 2017-06-30
4 | Mars | 2 | 2016-10-23 | 2017-02-04 | 100% | 125000 | 125000 | bar: 2016-10-31 to 2017-01-31
5 | Jupiter | 1 | 2016-10-23 | 2017-10-31 | 22.9% | 50000 | 5000 | bar: 2016-10-31
6 | Saturn | 2 | 2016-10-23 | 2018-03-15 | 28% | 450000 | 100000 | bar: 2016-10-31 to 2017-01-31
7 | Neptune | 1 | 2016-10-23 | 2018-07-31 | 24% | 200000 | 30000 | bar: 2016-10-31 to 2016-11-30
8 | Uranus | 3 | 2016-10-23 | 2018-12-31 | 22% | 100000 | 20000 | bar: 2016-10-31 to 2017-03-31
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
Here is a handy sheet to keep track of the projects in your portfolio. Set the Portfolio Start date in cell I2. The months shown in the table will update automatically, starting with the first month of your portfolio in cell N1. Populate the project data in the table, dragging down to expand if required.
Cells are filled based on the start and end date of the project. The % Complete column is used to fill the percentage of the project that has been completed in RED.
As we all know, the % Complete and the percentage of budget spent can differ from each other. The tracker uses the '$' symbol to indicate how much of the project budget has been spent. Based on the sample data this sheet is populated with, we can see that project Mercury is half complete, but has spent only 10% of its budget. Conversely, the Earth project has spent nearly all its Budget, but the red fill clearly shows they have a long way to go before the work is completed.
The sheet uses conditional formatting to colour the cells and uses the 'Fill' option under the alignment tab of the 'Format Cells' window to fill the cells with dollar signs, based on the cells' formulae.